## Crosswalk_June 2024
Percentages applied to CIPs |  |  |  | Percentage of Ordinance is weighted average of all CIPs related to Ordinance No. | [6 empty] | Explanation if original Pledge was not met |  | Do we want to make a recommendation for a TransNet Ordinance Amendment?
0-30 |  | ENV |  | Open to Traffic | Y - green flag/check
15-30 |  | Design |  |  | If not complete then %
30-60 |  | Early CON
60-90 |  | Late CON
90-100 |  | Final closeout, but open to traffic
TransNet Ordinance Crosswalk
As of June 2024
Oridnance No. | Completed or Remaining? | CIP No. | Project Name | Limits | Scope/Improvement | Ordinance/ CIP Completion Percentage | Initial TransNet Cost ($2002) | CIP Funds (millions) | TransNet Funds (millions) | Other Funds (millions) | Comments on Completion % | 2021 Plan ID No. | 2021 RP Scope | Comments on RP Mapping
1 |  |  | I-15: SR 163 to SR 56 | SR 163 - SR 56 | Add 4 managed lanes on the I-15 from SR 163 to SR 56. | 99.1% | 220 |  |  |  |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 6.
| Completed Projects | 1201501 | I-15 Express Lanes South Segment | I-15 from SR 163 to SR 56. | Construct four express lanes with moveable median barrier. | 100% |  | 330.08 | 42.575 | 287.505 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 6.
|  | 1201502 | I-15 Express Lanes Middle Segment | On I-15 from SR 56 to Centre City Parkway. | Construct four express lanes, moveable median barrier, and direct access ramps at Ted Williams Parkway and Rancho Bernardo Road. | 100% |  | 464.003 | 31.9094 | 432.0936 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 6.
| Remaining Ordinance Projects | 1201520 | I-15 Express Lanes – Forrester Creek Improvements | Near intersection of SR-125/SR-52 at Mission Gorge Rd., in the city of Santee. | Mitigation for impacts from the I-15 Managed Lanes Project, SR 52 Extension Project, San Diego Culvert Rehabilitation Project, and I-805 Culvert Replacement Project. Mitigation includes wetland creation, restoration and enhancement. | 10% |  | 1.122 | 1.122 | 0 | Special case where environmental mitigation was split into it's own CIP. Project represents 1% of overall project completion status. Mitigation is 10% complete. | N/A | N/A | Not included in Appendix A
2 |  |  | I-15: Centre City Pkwy to SR 78 | Centre City Parkway - SR 78 | Add 4 managed lanes on the I-15 from SR 78 to Centre City Parkway in Escondido. | 100% | 120 |  |  |  |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 6.
| Completed Projects | 1201503 | I-15 Express North Segment | On I-15 from Centre City Parkway to SR 78. | Construct four express lanes, fixed median barrier, and direct access ramps at Hale Avenue on I-15 | 100% |  | 177.797 | 40.898 | 136.899 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 6.
|  | 1201504 | I-15 FasTrak® | I-15 between SR 163 and SR 78. | Deploy electronic tolling equipment, operating system, and construct toll operations office and customer service center. | 100% |  | 27.2293 | 26.3643 | 0.86502 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 6.
3 |  |  | I-15: SR 94 to SR 163 | SR 94 - SR 163 | Add 2 high-occupancy vehicle (HOV) lanes on I-15 from SR 94 to SR 163. | 40% | 200 |  |  |  |  | CC012, CC013 | CC012: I-15 (I-805 to I-8)--transition from 8 freeway lanes +2 toll lanes to 6 freeway lanes+2 toll lanes+2 managed lanes CC013: I-15 (I-8 to SR 163)--transition from 8 freeway lanes to 6 freeway lanes+4 managed lanes
| Completed Projects | 1280514 | I-805/SR 15 Interchange | On I-805 from SR 94 to SR 15. | Design two HOV lanes and direct connectors between I-805 and SR 15 for northbound-to-northbound and southbound-to-southbound HOV/bus rapid transit traffic. | 100% |  | 17.926 | 17.926 | 0 | Project is 100% complete through design phase, which represents 40% of total project scope. | N/A | N/A | Project completed prior to 2015 Regional Plan.
| Remaining Ordinance Projects | 1601501 | CMCP - High Speed Transit/I-15 | Along the I-15 corridor from SR 76 to I-805. | Comprehensive Multimodal Corridor Plan for increasing transportation options, decreasing congestion, and improving travel times. | 0% |  | 1.5 | 0 | 1.5 | Future CIP scheduled to begin in FY 2026. | N/A | N/A | Not included in Appendix A
|  | TBD | I-15: SR 94 to SR 163 HOV (Construction) | On I-15 from SR 94 to SR 163. | Construct two HOV lanes on I-15 from SR 94 to SR 163. | 0% |  | TBD | 0 | 0 | Project has not begun so no progress to date to report. | CC012, CC013 | CC012: I-15 (I-805 to I-8)--transition from 8 freeway lanes +2 toll lanes to 6 freeway lanes+2 toll lanes+2 managed lanes CC013: I-15 (I-8 to SR 163)--transition from 8 freeway lanes to 6 freeway lanes+4 managed lanes
|  | TBD | I-805/SR 15 Interchange (Construction) | On I-805 from SR 94 to SR 15. | Construct direct connectors between I-805 and SR 15. | 0% |  | TBD | 0 | 0 | Project has not begun so no progress to date to report. | N/A | N/A | Not included in Appendix A
4 |  |  | HOV Connector: I-15 / SR 78 | I-15 - SR 78 | Add a HOV lane connector at the I-15/SR 78 interchange. | 12.5% | 200 |  |  |  |  | CC073 | CC073: I-15 (SR 78)--East to South and North to West Managed Lane Connector
| Remaining Ordinance Projects | 1207802 | I-15/ SR 78 HOV Connectors | On SR 78 and I-15 from Twin Oaks Valley Road to West Valley Parkway. | Final environmental document and design for HOV/ML direct connectors at SR 78 and I-15 for northbound-to-westbound and eastbound-to-southbound traffic and managed lanes between the connector and Twin Oaks Valley Road. | 12.5% |  | 39.937 | 4.207 | 35.73 | Environmental phase is 75% complete. Overall project completion is 13%. | CC073 | CC073: I-15 (SR 78)--East to South and North to West Managed Lane Connector
|  | TBD | I-15/ SR 78 HOV Connectors (Construction) | On SR 78 and I-15 from Twin Oaks Valley Road to West Valley Parkway | Construction for HOV/ML direct connectors at SR 78 and I-15 for northbound-to-westbound and eastbound-to-southbound traffic and managed lanes between the connector and Twin Oaks Valley Road. | 0% |  | TBD | 0 | 0 | Construction will begin upon completion of final environmental document and design under CIP 1207802. | CC073 | CC073: I-15 (SR 78)--East to South and North to West Managed Lane Connector
5 |  |  | HOV Connector: I-15 / SR 94 | I-15 - SR 94 | Add a HOV lane connector at the I-15/SR 94 interchange. | 15% | 150 |  |  |  |  | CC032 | CC032: SR 94 (I-5 to I-15)--8 freeway lanes to 6 freeway lanes and 3 managed lanes
| Completed Projects | 1280508 | SR 94 Express Lanes I-805 to Downtown | On SR 94 from I-5 to I-805. | Final environmental document for HOV lanes in the median of SR-94, including direct connectors between I-805 and SR-94 for northbound-to-westbound and eastbound-to-southbound and between SR-94 and SR-15 for eastbound-to-northbound and southbound-to-westbound HOV/Rapid traffic. | 100% |  | 22.1 | 12.1 | 10 | Project scope is through environmental clearance phase. Project now part of SR 94 Transit Priority Lanes (I-805 to I-5) under CIP 1280518. | CC032, CC033 | CC032: SR 94 (I-5 to I-15)--8 freeway lanes to 6 freeway lanes and 3 managed lanes CC033: SR 94 (I-15 to I-805)--8 freeway lanes to 6 freeway lanes and 3 managed lanes
| Remaining Ordinance Projects | TBD | HOV Connector: I-15 / SR 94 (Design and Construction) | I-15/SR 94 interchange. | Design and construction of HOV lane connector. | 0% |  | TBD | 0 | 0 | Project has not begun so no progress to date to report. | CC032, CC033 | CC032: SR 94 (I-5 to I-15)--8 freeway lanes to 6 freeway lanes and 3 managed lanes CC033: SR 94 (I-15 to I-805)--8 freeway lanes to 6 freeway lanes and 3 managed lanes
6 |  |  | SR 94: I-5 to I-15 | I-5 - I-15 | Add two HOV lanes on SR 94 from I-5 to I-15. | 15% | 80 |  |  |  |  | CC032, CC033 | CC032: SR 94 (I-5 to I-15)--8 freeway lanes to 6 freeway lanes and 3 managed lanes CC033: SR 94 (I-15 to I-805)--8 freeway lanes to 6 freeway lanes and 3 managed lanes
| Completed Projects | 1280508 | SR 94 Express Lanes I-805 to Downtown | On SR 94 from I-5 to I-805. | Final environmental document for HOV lanes in the median of SR-94, including direct connectors between I-805 and SR-94 for northbound-to-westbound and eastbound-to-southbound and between SR-94 and SR-15 for eastbound-to-northbound and southbound-to-westbound HOV/Rapid traffic. | 100% |  | 22.1 | 12.1 | 10 | Project scope is through environmental clearance phase. Project now part of SR 94 Transit Priority Lanes (I-805 to I-5) under CIP 1280518. | CC032, CC033 | CC032: SR 94 (I-5 to I-15)--8 freeway lanes to 6 freeway lanes and 3 managed lanes CC033: SR 94 (I-15 to I-805)--8 freeway lanes to 6 freeway lanes and 3 managed lanes
| Remaining Ordinance Projects | TBD | SR 94 HOV Lanes: I-5 to I-15 | On SR 94 from I-5 to I-15. | Design and construction of 2 HOV lanes. | 0% |  | TBD | 0 | 0 | Project has not begun so no progress to date to report. | CC032 | SR 94 (I-5 to I-15)--8 freeway lanes to 6 freeway lanes and 3 managed lanes
7 |  |  | BRT Route 610: via I-15 / SR 94 (Now Route 235) | I-15/ SR 94 | Building and upgrading 6 Bus Rapid Transit stations, upgrades to downtown stations, building Direct Access Ramps in 4 locations, and implementing 10 minute peak service by 2010 and 15 minute off-peak service by 2030. | 73.89% | 520 |  |  |  |  | TL29, CC110 | TL29: Rapid 235, Escondido to Downtown San Diego via I-15 (Direct Access Ramp stations) CC110: I-15 (Clairemont Mesa Boulevard) Direct Access Ramp, North and South
| Completed Projects | 1201505 | I-15 BRT Stations: Rancho Bernardo, Sabre Springs, and Del Lago | Along I-15 at Rancho Bernardo Road, Sabre Springs Parkway, and Del Lago Boulevard. | Construct transit stations, surface parking, bus staging areas, bike lockers, and station amenities for I-15 BRT service. | 100% |  | 49.544 | 16.654 | 32.89 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1201506 | I-15 Mira Mesa Direct Access Ramp - Bus Rapid Transit Station | Along I-15 from Carroll Canyon Road to Mira Mesa Boulevard. | Construct direct access ramps, transit station with bus staging platforms, bike lockers, and station amenities. | 100% |  | 54.68 | 27.186 | 27.494 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1201508 | I-15 Bus Rapid Transit | From Escondido to Downtown San Diego via I-15 and SR 94. From Escondido to Sorrento Valley via I-15 and Mira Mesa Boulevard. | New BRT service including vehicle acquisition. | 100% |  | 33.881 | 23.675 | 10.206 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1201509 | Downtown BRT Stations | Along Broadway Street in San Diego. | New and modified transit stops at Park Boulevard, 11th Avenue, India Street, and Kettner Boulevard. | 100% |  | 20.844 | 20.84 | 0.004 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1201512 | I-15 BRT Sabre Springs Parking Structure | Along I-15 at Sabre Springs transit station. | Construct five hundred-car parking structure, 150 surface spaces, bus staging area (eight-bus capacity), landscaping, lighting, modular bus station, security cameras, bus shelters, and amenities. | 100% |  | 14.424 | 14.424 | 0 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1201516 | I-15 BRT Station Enhancements |  |  | 100% |  |  |  | 0
|  | 1201517 | BRT Wi-Fi Phase I | MTS Rapid Bus routes 235 (from Escondido to Downtown San Diego along I-15 and SR 94), 237 (from Escondido to UC San Diego along I-15, Mira Mesa Boulevard and La Jolla Village Drive), and 215 (from San Diego State University to Downtown San Diego along El Cajon Boulevard, College Avenue, Park Boulevard, and Broadway). | Feasibility analyses of hardware procurement, testing, and installation for WiFi on buses pilot and a possible full implementation project to serve Rapid routes. | 100% |  | 0.15106 | 0.15106 | 0 | Initial analyses were conducted, but technology was proven to not be cost effective and thus full implementation did not occur. | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 53.
| Remaining Ordinance Projects | 1201514 | Downtown Multiuse and Bus Stopover Facility | The block bounded by A Street, B Street, State Street, and Union Street in the Columbia-Civic/Core neighborhood of Downtown San Diego. | Preliminary engineering, design, and right-of-way activities for a bus stopover facility and potentially a multiuse facility that could include office, residential, and retail development. | 15% |  | 57.98 | 36.29 | 21.69 | Project is currently acquring ROW only. | N/A | N/A | Not included in Appendix A
|  | 1201515 | Clairemont Mesa Blvd BRT Stations | On Clairemont Mesa Boulevard from SR 163 to I-15. | Traffic Signal Priority on Clairemont Mesa Boulevard and transit station improvements at eastbound Ruffin Road stop. Final design and construction of five additional transit stations. | 50% |  | 1.665 | 1.665 | 0 | Improvements are complete for 1 out of 6 transit stations is complete (100% complete). Remaining 5 stations are fully designed and pending additional funds to complete construction (40% complete). | TL29 | TL29: Rapid 235, Escondido to Downtown San Diego via I-15 (DAR stations)
|  | 1201519 | I-15 Transit Priority Lanes and Direct Access Ramp at Clairemont Mesa Blvd. | Along the I-15 from I-8 to SR-163. | Environmental clearance and design for two transit lanes and a south facing Direct Access Ramp (DAR) at Clairemont Mesa Boulevard. | 0% |  | 28 | 0 | 28 |  | CC110 | CC110: I-15 (Clairemont Mesa Boulevard) Direct Access Ramp, North and South
8 |  |  | BRT Route 470: via I-15 / Mira Mesa Blvd (Now Route 237) | Escondido Transit Center | Adding a new bus rapid transit route from Escondido to Sorrento Mesa using Route 610 stations and direct access ramps. Adding 15 min peak service from Escondido by 2016. | 100% | 150 |  |  |  |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 53.
| Completed Projects | 1201511 | Mira Mesa Blvd BRT Priority Treatments | On Mira Mesa Boulevard from I-15 to UC San Diego. | Traffic Signal Priority measures and preliminary engineering for queue jumpers and new bus shelters. Signage and communications plan for Park and Ride. | 100% |  | 3.402 | 3.402 | 0 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 53.
|  | 1201518 | I-15 Mira Mesa Transit Station Parking Structure | Along I-15 from Carroll Canyon Road to Mira Mesa Boulevard. | Reimburse San Diego Miramar College for the construction of parking garage in order to provide Park and Ride near the transit center. | 100% |  | 9.507 | 9.507 | 0 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 53.
9 |  |  | I-805: SR 905 to SR 54 | SR 905 - SR 54 | Adding 2 reversible HOV lanes on I-805 from SR 905 to SR 54. | 15% | 150
| Completed Projects | 1280501 | I-805 South 4 Express Lanes | On I-805 from Palomar Street to Landis Street. | Final environmental document for four express lanes in the median, Direct Access Ramp (DAR) at Palomar Street, center-line Bus Rapid Transit (BRT) stations at H Street and Plaza Blvd, direct freeway-to-freeway HOV connectors between I-805 and I-15. | 100% |  | 27.657 | 19.364 | 8.293 | Project is 100% complete through environmental phase, which represents 15% of total project scope. | N/A | N/A | Project was completed prior to 2015 Regional Plan.
| Remaining Ordinance Projects | 1280515 | I-805 South Soundwalls | Along I-805 from Palomar Street to SR 54. | Construct soundwalls (Units 1 and 2) and Sweetwater River Bridge improvements. | 73% |  | 114.092 | 14.388 | 99.704 | Construction of Unit 1 soundwalls and Sweetwater River Bridge improvements is complete. Construction of Unit 2 soundwalls is 10% complete. | N/A | N/A | Not included in Appendix A
|  | TBD | I-805 HOV Lanes Construction | I-805 from SR 905 to SR 54 | Design and construction of 2 HOV lanes. | 0% |  | 0 | 0 | 0 | Design and construction has not begun so no progress to date to report. | CC016, CC017, CC018 | CC016: I-805 (SR 905 to Palm Avenue)--8 freeway lanes to 6 freeway lanes and 4 managed lanes CC017: I-805 (Palm Ave to H Street)--converting 2 freeway lanes to 2 managed lanes CC018: I-805 (H Street to I-15)--converting 2 freeway lanes to 2 managed lanes
10 |  |  | I-805: SR 54 to I-8 | SR 54 - I-8 | Adding 4 managed lanes on the I-805 from SR 54 to I-8. | 50% | 450 |  |  |  |  | CC018, CC019 | CC018: I-805 (H Street to I-15)--converting 2 freeway lanes to 2 managed lanes CC019: I-805 (SR 15 to I-8)--convert 2 freeway lanes to 2 managed lanes, add 2 new managed lanes
| Completed Projects | 1280510 | I-805 South: 2 HOV and Direct Access Ramp | On I-805 from Palomar Street to SR 94. | Construct two HOV lanes between Palomar Street and SR 94, north-facing Direct Access Ramps (DAR) and transit station at Palomar Street, and general purpose lanes between Plaza Boulevard and SR 54. | 100% |  | 182.546 | 122.829 | 59.717 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 6-7.
| Remaining Ordinance Projects | 1280521 | I-805 South: HOV Conversion to Express Lanes (Palomar to SR94) | From East Palomar Street, on the south, to SR 94, on the north. | Design for the conversion of 11 miles of existing carpool lanes to express managed lanes. | 0% |  | 11 | 1 | 10 | Project will begin in FY 2025. | CC017, CC018 | CC017: I-805 (Palm Avenue to H Street)--converting 2 freeway lanes to 2 managed lanes. CC018: I-805 (H Street to I-15)--converting 2 freeway lanes to 2 managed lanes.
|  | TBD | I-805 South: HOV Lanes (SR 94 to I-8) | On I-805 from SR 94 to I-8 | Construct two HOV lanes between SR 94 and I-8. | 0% |  | 0 | 0 | 0 | Project has not begun so no progress to date to report. | CC018, CC019 | CC018: I-805 (H Street to I-15)--converting 2 freeway lanes to 2 managed lanes. CC019: I-805 (SR 15 to I-8)--convert 2 freeway lanes to 2 managed lanes, add 2 new managed lanes
11 |  |  | I-805: Mission Valley Viaduct | Mission Valley Viaduct | Adding 4 managed lanes on the I-805 near the Mission Valley Viaduct. | 0% | 250 | 0 | 0 | 0 | Project has not begun so no progress to date to report. | CC020 - CC022 | CC020: I-805 (I-8 to Mesa College Drive)--convert 10 freeway lanes to 6 freeway lanes and 4 managed lanes CC021: I-805 (Mesa College Drive to Balboa Avenue)--convert 2 freeway lanes to 2 managed lanes, add 2 new managed lanes CC022: I-805 (Balboa Avenue to Northbound Bypass Lane)--convert 2 freeway lanes to 2 managed lanes
12 |  |  | I-805: I-8 to I-5 | I-8 - I-5 | Adding 4 managed lanes on the I-805 from I-8 to I-5. | 51.42% | 380 |  |  |  |  | CC120, CC020 - CC022 | CC120: I-805 Active Transportation and Demand Management CC020: I-805 (I-8 to Mesa College Drive)--convert 10 freeway lanes to 6 freeway lanes and 4 managed lanes CC021: I-805 (Mesa College Drive to Balboa Avenue)--convert 2 freeway lanes to 2 managed lanes, add 2 new managed lanes CC022: I-805 (Balboa Avenue to Northbound Bypass Lane)--convert 2 freeway lanes to 2 managed lanes
| Completed Projects | 1280503 | I-805 North 4 Express Lanes | I-805 from SR 52 to I-5 merge. | Final environmental document for 4 managed lanes. | 100% |  | 11.609 | 9.834 | 1.775 | Project scope is through environmental clearance only. | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1280505 | I-805 HOV/Carroll Canyon DAR | On I-805 from Carroll Canyon Road to I-5 in Sorrento Valley. | Construct two HOV lanes and north facing Direct Access Ramp (DAR) at Carroll Canyon Road, and extend Carroll Canyon Road as a four-lane arterial from Scranton Road to Sorrento Valley Road. | 100% |  | 95.775 | 32.465 | 63.31 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1280511 | I-805 North: 2 HOV Lanes | On I-805 from SR 52 to Carroll Canyon Road. | Construct two HOV lanes and a south-facing direct access ramp (DAR) at Carroll Canyon Road. | 100% |  | 111.49 | 7.705 | 103.785 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 7.
| Remaining Ordinance Projects | 1280516 | I-805 North Auxiliary Lanes | Along I-805 from SR 52 to Nobel Drive. | Design and construct one northbound and one southbound auxiliary lane. | 55% |  | 31.517 | 0.721 | 30.796 | Construction is 25% complete. Overall project is 55% complete since design and final environmental document have been completed. | N/A | N/A | Not included in Appendix A
|  | 1280517 | I-805 HOV Conversion to Express Lanes | On I-805 from SR 52 to the I-5/805 merge. | Construction to convert HOV lanes to Express Lanes. | 0% |  | 86.3 | 1.3 | 85 | Future CIP scheduled to begin in FY 2026. | CC022 | CC022: I-805 (Balboa Avenue to Northbound Bypass Lane)--convert 2 freeway lanes to 2 managed lanes
|  | 1280519 | I-805 Transit Priority Lanes (SR 15 to SR 52) | On I-805 from SR-15 to SR 52. | Final environmental document for two additional transit priority lanes between SR-15 and SR-52 and restripe of the viaduct over Mission Valley. | 5.7% |  | 30 | 24 | 6 | Environmental document is 7% complete. Overall project is 6% complete when considering future design and construction. | CC019 - CC022 | CC019: I-805 (SR 15 to I-8)--convert 2 freeway lanes to 2 managed lanes, add 2 new managed lanes CC020: I-805 (I-8 to Mesa College Drive)--convert 10 freeway lanes to 6 freeway lanes and 4 managed lanes CC021: I-805 (Mesa College Drive to Balboa Avenue)--convert 2 freeway lanes to 2 managed lanes, add 2 new managed lanes CC022: I-805 (Balboa Avenue to Northbound Bypass Lane)--convert 2 freeway lanes to 2 managed lanes
13 |  |  | I-805 / SR 54 Interchange Improvements | I-805 and SR 54 Interchange | Various improvements at the I-805/SR 54 interchange. | 60.62% | 10 |  |  |  |  | CC093 | CC093: I-805/SR 54 managed lane connector (MLC), south to east and west to north
| Completed Projects | 1280506 | I-805 Auxiliary Lanes | In Chula Vista from SR 54 to E Street. | Widen I-805 and construct southbound auxiliary lane. | 100% |  | 13.768 | 0 | 13.768 |  | N/A | N/A | Not included in Appendix A
| Remaining Ordinance Projects | 1280520 | I-805/SR 94/SR 15 Transit Connection | On I-805 from SR 94 to SR 15 | Design and right-of-Way for two HOV lanes and transit connectors between I-805 and SR 15 for northbound to northbound and southbound to southbound HOV and Rapid connection. | 21.25% |  | 16 | 0 | 16 | Design is 25% complete. Overall project is 21% complete. | CC018, CC083, CC084 | CC018: I-805 (H Street to I-15)--converting 2 freeway lanes to 2 managed lanes. CC083: I-805/SR 14 MLC, north to north and south to south CC084: I-805/SR 94 MLC, north to west and east to south
14 |  |  | BRT Route 628: via I-805 / I-15 / SR 94 (Now known as South Bay Rapid) | I-805 / I-15 / SR 94 | Building 13 stations and Direct Access Ramps in 4 locations. Adding 15 min peak / 30 min off-peak service by 2010 and 10 min peak / 15 min off-peak service by 2020. | 100% | 500 |  |  |  |  | N/A | N/A | Projects completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 14.
| Completed Projects | 1201513 | South Bay BRT Maintenance Facility | At South Bay Maintenance Facility on Main Street in Chula Vista. | Expansion of the South Bay Maintenance Facility to accommodate maintenance of bus Rapid transit vehicles, including property acquisition, site preparation, lighting, parking, fencing, and bus servicing facilities. | 100% |  | 59.991 | 30.898 | 29.093 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1280504 | South Bay BRT | From the Otay Mesa Border Crossing to Downtown San Diego along SR 125, Palomar Street, I-805, and SR 94. | Develop new Rapid transit service from the I-805/Palomar Direct Access Ramp to the Otay Mesa Border, including the construction of a guideway on East Palomar over SR 125, around Otay Ranch Town Center Mall and through the Millenia development. Construct seven new Rapid stations. | 100% |  | 127.391 | 105.9791 | 21.4119 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 14.
|  | 1280512 | I-805 Imperial BRT Station | On I-805 just north of Imperial Avenue. | Prepare final Project Study Report-Project Development Supports (PSR-PDS) and Preliminary Environmental Assessment Report (PEAR) for an I-805 bus rapid transit station with connection to the 47th Street Trolley Station. | 100% |  | 1.673 | 1.673 | 0 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1685501 | CMCP - South Bay to Sorrento Corridor | From the U.S.-Mexico Border along SR 11, SR 905, I-5, and I-805 to SR 94, then along I-805 and SR 15/I-15 to SR 52, then along I-805 to the I-5/I-805 Merge. | Oversight of utilization of data in transportation planning and development of an innovative transportation network by evaluating all travel modes and transportation facilities in this highly congested corridor. The study subareas include the communities of Sorrento Valley, Kearny Mesa, Mission Valley, National City, Chula Vista, Coronado/Imperial Beach, and U.S./Mexico Border. | 100% |  | 4.9798 | 3.1648 | 1.815 |  | N/A | N/A | Not included in Appendix A
14 |  |  | BRT Route 628: via I-805 / I-15 / SR 94 (Now known as South Bay Rapid) | I-805 / I-15 / SR 94 | Building 13 stations and Direct Access Ramps in 4 locations. Adding 15 min peak / 30 min off-peak service by 2010 and 10 min peak / 15 min off-peak service by 2020. | 97.5% | 120 |  |  |  |  | CC019 | CC019: I-805 (SR 15 to I-8)--convert 2 freeway lanes to 2 managed lanes, add 2 new managed lanes
| Completed Projects | 1280507 | VAA/Bus on Shoulder | On I-805 corridor, between National City and 8th Street Trolley Centers and Sorrento Valley. | Start express bus service on inside shoulder of I-805. | 100% |  | 1.1446 | 0.22892 | 0.91569 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
| Remaining Ordinance Projects | 1280513 | I-805/SR 94 Bus on Shoulder Demonstration Project | In Chula Vista, on East Palomar Street between Heritage Road and I-805. On I-805 between East Palomar Street and SR 94. On SR 94 between I-805 and Downtown San Diego. | Design and construct new freeway shoulder infrastructure on East Palomar, I-805 and SR 94. Implement technology improvements within the corridor to support Rapid operation. Procurement of 16 new compressed natural gas buses. | 95% |  | 30.9 | 16.816 | 14.084 | Project is open to public and working towards completion of Construction Complete milestone. | CC019 | CC019: I-805 (SR 15 to I-8)--convert 2 freeway lanes to 2 managed lanes, add 2 new managed lanes
15 |  |  | SR 94: I-805 to I-15 | I-805 - I-15 | Add 2 HOV lanes on SR 94 from I-805 to I-15. | 4.95% | 70 |  |  |  |  | CC033 | CC033: SR 94 (I-15 to I-805)--8 freeway lanes to 6 freeway lanes+3 managed lanes
| Remaining Ordinance Projects | 1280518 | SR 94 Transit Priority Lanes (I-5 to I-805) | On SR 94 from I-5 to I- 805. | Environmental studies for two transit priority lanes and/or a transit priority connector along SR 94 from I-805 to I-5. | 4.95% |  | 0.8 | 0.8 | 0 | Initial feasibility/environmental studies are 99% complete. | CC033 | CC033: SR 94 (I-15 to I-805)--8 freeway lanes to 6 freeway lanes +3 managed lanes
16 |  |  | BRT Route 680: via I-805 / I-15 / SR 52 | I-805 / I-15 / SR 52 | Build 1 new station using Direct Access Ramps and stations built by routes 610 and 628. Also, adding 15 min peak service by 2015 and 10 min peak service by 2030. | 0% | 120 | 0 | 0 | 0 | Project has not begun so no progress to date to report. | TL02, TL03 | TL02: Commuter Rail 582 (Purple Line), Sorrento Mesa to National City via UTC, Kearny Mesa, and University Heights TL03: Commuter Rail 582 (Purple Line), National City to U.S. Border
17 |  |  | SR 52: I-15 to I-805 | I-15 - I-805 | Add 2 HOV lanes on SR 52 from I-15 to I-805. | 0% | 70 | 0 | 0 | 0 | Project has not begun so no progress to date to report. | CC029 | CC029: SR 52 (I-805 to I-15)-- 6 freeway lanes to 4 freeway lanes and 3 managed lanes
18 |  |  | HOV Connector: I-805 / SR 52 Interchange | I-805 - SR 52 | Addition of a HOV lane connector for the I-805/SR 52 interchange. | 0% | 150 | 0 | 0 | 0 | Project has not begun so no progress to date to report. | CC085, CC086 | CC085: I-805/SR 52 MLC, west to north and south to east CC086: I-805/SR 52 MLC, north to west and east to south
19 |  |  | I-5: SR 905 to SR 54 | SR 905 - SR 54 | Add 2 HOV lanes on I-5 from SR 905 to SR 54. | 0% | 130 | 0 | 0 | 0 | Project has not begun so no progress to date to report. | CC001, CC002 | CC001: I-5 (SR 905 to H Street)--8 freeway lanes to 6 freeeway lanes+2 managed lanes CC002: I-5 (H Street to Pacific Hwy)--8 freeway lanes to 6 freeeway lanes+4 managed lanes
20 |  |  | I-5: SR 54 to I-8 | SR 54 - I-8 | Add 2 HOV lanes on I-5 from SR 54 to I-8. | 4.5% | 600 |  |  |  |  | CC002 | CC002: I-5 (H Street to Pacific Hwy)--8 freeway lanes to 6 freeeway lanes+4 managed lanes
| Completed Projects | 1600503 | CMCP - Central Mobility Hub: Military Installation Resilience (OEA Grant) | Central Mobility Station/I-5/Coronado Connection & Downtown Connections to Naval Bases Coronado, Point Loma and San Diego. | The project aims to assess vulnerabilities such as sea-level rise, wildfires, supporting land uses and their potential impacts on mission readiness to support work underway on the Central Mobility Hub in the San Diego region. This work effort is supporting the Comprehensive Multimodal Corridor Plan (CMCP) for Central Mobility Connections (CIP No. 1600504) and will be incorporated into regional and military installation planning efforts. | 100% |  | 0.87539 | 0.084 | 0.79139 |  | N/A | N/A | Not included in Appendix A
|  | 1600505 | CMCP - Central Mobility Hub: Military Installation Resilience (OEA Grant) - Phase 2 | Central Mobility Station/I-5/Coronado Connection and Downtown Connections to Naval Bases Coronado, Point Loma and San Diego. | Oversight of utilization of data in transportation planning and development the Comprehensive Multimodal Corridor Plan for Central Mobility Connections (CIP No. 1600504) and will be incorporated into regional and military installation planning efforts. Assess vulnerabilities such as sea-level rise, wildfires, supporting land uses and their potential impacts on mission readiness to support work underway on the Central Mobility Hub in the San Diego region. | 100% |  | 0.967 | 0 | 0.967 |  | N/A | N/A | Not included in Appendix A
|  | 1600501 | CMCP - Central Mobility Hub - Notice of Preparation/P3 Procurement | Area bound by Rosecrans Street, I-5, Grape Street, and Harbor Drive. | Notice of Preparation (NOP), preliminary project alternatives development, and Public-Private Partnership (P3) procurement for Central Mobility Hub, Automated People Mover, roadway/freeway modifications, and supportive multi-use development. | 100% |  | 5.714 | 0.5 | 5.214 |  | N/A | N/A | Not included in Appendix A
| Remaining Ordinance Projects | 1600504 | CMCP – Central Mobility Connections | Central Mobility Station/I-5/Coronado Connection & Downtown Connection. | Oversight of utilization of data in transportation planning and development of innovative transportation solutions to transform the way people and goods move in the area of San Diego International Airport and the surrounding communities, including the proposed development of a Central Mobility Hub and Connections CMCP. In addition, this project will analyze the feasibility of new rail grade separations along the railway corridor between Old Town and Downtown. | 60% |  | 4.833 | 0.95 | 3.883 | Initial CMCP report is complete. Work on feasbility of rail grade separations will begin in FY 2025. | N/A | N/A | Not included in Appendix A
|  | TBD | I-5: SR 54 to I-8 (Consruction) | I-5 from SR 54 to I-8 | Final environmental clearance, design, and construction of 2 HOV lanes on I-5 from SR 54 to I-8. | 0% |  | 0 | 0 | 0 | Only initial CMCP studies have been completed. Environmental clearance has not begun. | CC002 | CC002: I-5 (H Street to Pacific Hwy)--8 freeway lanes to 6 freeeway lanes+4 managed lanes
21 |  |  | I-5: I-8 to I-805 | I-8 - I-805 | Add 2 HOV lanes on I-5 from I-8 to I-805, and environmental and preliminary engineering for I-5/I-8 interchange improvements. | 50% | 193 |  |  |  |  | CC003, CC004 | CC003: I-5 (Pacific Hwy to SR 52)--8 freeway lanes to 6 freeway lanes+4 managed lanes CC004: I-5 (SR 52 to I-805)--8 freeway lanes to 6 freeway lanes+4 managed lanes
| Completed Projects | 1200505 | I-5/I-8 West to North Connector Improvements | On I-5 from I-8 to Sea World Drive. | Widen west to north connector and construct new northbound lane. | 100% |  | 16.338 | 1.545 | 14.793 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1200506 | I-5/Genesee Interchange and Widening | On I-5 from Voigt Drive to Sorrento Valley Road. | Construct longer and wider bridge and replace ramp connections on Genesee Avenue, construct retaining walls and a bike path between Voigt Drive and Sorrento Valley Road, and complete the follow-up landscaping project. | 100% |  | 121.278 | 20.101 | 101.177 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 29.
|  | 1200507 | I-5/Voigt Drive Improvements | On I-5 at the Voigt Drive overcrossing from Gilman Drive on the west side to Genesee Avenue on the east side. | Construction of the realignment of both Campus Point and Voigt Drive between I-5 and Genesee Avenue. | 100% |  | 41.015 | 23.405 | 17.61 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 29.
|  | 1200508 | I-5/Gilman Drive Bridge | On I-5 between La Jolla Village Drive and the Voigt Drive overcrossing. | Construct new overcrossing over I-5 between Gilman Drive and Medical Center Drive. | 100% |  | 24.757 | 15 | 9.757 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 6.
| Remaining Ordinance Projects | TBD | I-5: I-8 to I-805 | On I-5 from Sea World Drive to I-805 | Add HOV lane on I-5 from Sea World Drive to I-805. | 0% |  | 0 | 0 | 0 | Project has not begun so no progress to date to report. | CC003, CC004 | CC003: I-5 (Pacific Hwy to SR 52)--8 freeway lanes to 6 freeway lanes+4 managed lanes CC004: I-5 (SR 52 to I-805)--8 freeway lanes to 6 freeway lanes+4 managed lanes
22 |  |  | Route 500 (Blue Line Trolley) Improvements | Downtown San Diego to the San Ysidro border crossing | Conversion to low-floor vehicles, enhanced stations, signal upgrades, extended platforms, and grade separations in Chula Vista. Also, 7.5 min peak / 7.5 min off-peak service by 2020. | 83.8% | 270 |  |  |  |  | TL12, TL13 | Blue Line Improvements
| Completed Projects | 1210010 | Orange and Blue Line Project Management | On trolley system from Old Town Transit Center, La Mesa Station, San Ysidro Station to downtown San Diego. | Coordinate budget, schedule, environmental clearance, permitting, design, construction, and construction management for conversion to low-floor vehicles and system renewal. | 100% |  | 19.429 | 18.918 | 0.511 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1210020 | Blue Line Crossovers and Signals | Blue Line: from America Plaza to San Ysidro, Orange Line: from Santa Fe Depot to Grossmont, Green Line: from Old Town to 12th & Imperial. | New crossovers, signaling system, fiber optic connections, and relocation of catenary poles. | 100% |  | 40.84 | 10.412 | 30.428 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1210030 | Blue Line Station Rehab | Blue Line: from 12th & Imperial to San Ysidro. | Reconstruct station platforms for low-floor trolley vehicles and replace existing shelters. Install new rail, ties, grade crossings. Repair substations and wayside slopes. | 100% |  | 132.936 | 32.931 | 100.005 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1210040 | Orange and Blue Line Traction Power Substations | Blue Line: from America Plaza to San Ysidro, Orange Line: from Santa Fe Depot to Grossmont. | Install 17 new traction power substations; site improvements at stations and substations and network improvements. | 100% |  | 29.2 | 15.5044 | 13.6956 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1210050 | Orange and Blue Line Communications System | Blue Line: from America Plaza to San Ysidro; Orange Line: from Santa Fe Depot to Grossmont; Green Line: from Old Town to 12th & Imperial. | Install communications equipment including variable message signs, central control software, fiber optic cable, real-time next Trolley arrival signs, and closed-circuit television. | 100% |  | 5.979 | 4.992 | 0.987 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1210070 | Orange and Blue Line Platforms | Blue Line: from America Plaza to San Ysidro; Orange Line: from Santa Fe Depot to Grossmont; Green Line: from Old Town to 12th & Imperial. | Reconstruct station platforms for low-floor Trolley vehicles and replace existing shelters. Install a double crossover at America Plaza Station and replace switches and signaling system at Santa Fe Depot. | 100% |  | 69.216 | 32.072 | 37.144 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1210080 | Low Floor LRT Vehicles | Blue Line: from America Plaza to San Ysidro; Orange Line: from Santa Fe Depot to Grossmont; Green Line: from Old Town to 12th & Imperial. | 65 new low-floor trolley vehicles. | 100% |  | 269.057 | 36.921 | 232.136 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
| Remaining Ordinance Projects | 1210021 | Blue Line Railway Signal Improvements | Along the Blue Line trolley from 12th and Imperial to San Ysidro. | Railway signaling design work, software modifications, and construction of hardware modifications to provide pedestrian crossing improvements on Blue Line Grade Crossing. | 40% |  | 4.55 | 4.55 | 0 | Project is complete through environmental and design phases. Construction will begin in FY 2025. | TL12 | Blue Line Improvements
|  | 1210091 | Palomar Street Rail Grade Separation | Palomar Street and Industrial Boulevard in the City of Chula Vista. | Construction, design, and final environmental clearance for rail grade separation and relocation of utilities. | 12% |  | 34.135 | 5.695 | 28.44 | Environmental document is 70% complete. Overall project completion is 12% complete. | TL12, TL13 | Blue Line Improvements
23 |  |  | Route 570 (Mid Coast) | Old Town Transit Center to UTC | Extension of light rail transit from Old Town Transit Center to UTC via I-5 and UCSD. 15-minute all day service by 2020. | 100% | 780 |  |  |  |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 3.
| Completed Projects | 1041501 | Mid-Coast Light Rail Transit (LRT) | On and along existing rail corridor from Old Town to University of California, San Diego (UCSD)/University City. | Pre-preliminary engineering studies for an 11-mile trolley line with new transit stations proposed at Tecolote Road, Clairemont Drive, Balboa Avenue, Nobel Drive, UCSD West, UCSD East, Executive Drive, and the University Town Center (UTC) Transit Center. | 100% |  | 32.345 | 8.356 | 23.989 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 3.
|  | 1257001 | Mid-Coast Light Rail Transit (LRT) | On and along existing coastal rail corridor from Old Town Transit Center to Gilman Drive, along I-5 from Gilman Drive to UC San Diego, and along Voigt Drive and Genesee Avenue to UTC. | A new 10.9-mile extension of the Trolley Blue Line with stations at Tecolote Road, Clairemont Drive, Balboa Avenue, Nobel Drive, Veterans Administration Medical Center, Pepper Canyon and Voigt Drive on the UC San Diego campus, Executive Drive, and University Towne Center (UTC). | 100% |  | 2171.201 | 875.693 | 1295.508 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 3.
24 |  |  | Route 634 (SuperLoop) (Now known as Routes 201, 202, and 204) | University City | Signal priority, queue jumper lanes, other arterial improvements, vehicles, and stations. 10 minute all day service by 2010. | 100% | 140 |  |  |  |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
| Completed Projects | 1041502 | SuperLoop | In University City along Voigt Drive, Genesee Avenue, Nobel Drive, Gilman Drive, and Executive Drive. | New SuperLoop Rapid service, traffic signal priority measures, new signalized intersections, street modifications, new SuperLoop Rapid vehicles, and new enhanced transit stops. | 100% |  | 35.187 | 33.8493 | 1.3377 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
25 |  |  | I-5 / I-805 Merge | I-5/I-805 Merge | Add 4 managed lanes at the I-5/ I-805 merge. | 15% | 30 |  |  |  |  | CC005 | CC005: I-5 (I-805 to SR 56)--8F/14F+2HOV to 6F/12F+4ML (managed lanes)
| Completed Projects | 1200501 | I-5 North Coast: 4 Express Lanes | On I-5 from La Jolla Village Drive to Vandegrift Boulevard. | Final environmental document and Public Works Plan for four managed lanes including direct access ramps at various locations. | 100% |  | 74.2 | 28.601 | 45.599 | Final environmental clearance 100% complete. Overall project is 15% complete. | CC004 | CC004: I-5 (SR 52 to I-805)--8 freeway lanes to 6 freeway lanes+4 managed lanes
| Remaining Ordinance Projects | TBD | I-5 North Coast: 4 Express Lanes Construction | I-5/I-805 Merge | Design and construct 4 managed lanes at the I-5/ I-805 merge. | 0% |  | 0 | 0 | 0 | Construction has not begun so no progress to date to report. | CC005 | CC005: I-5 (I-805 to SR 56), 8F/14F+2HOV to 6F/12F+4ML
26 |  |  | I-5: SR 56 to Leucadia Blvd | SR 56 - Leucadia Blvd. | Add 4 managed lanes on the I-5 from SR 56 to Leucadia Boulevard. | 75% | 400 |  |  |  |  | CC006, CC007, CC046 | CC006: I-5 (SR 56 to Via de La Valle)--8/10 freeway lanes+2 HOV lanes to 6/8 freeway lanes+4 managed lanes CC007: I-5 (Via de La Valle to La Costa), 8 freeway lanes to 6 freeway lanes +4 managed lanes CC046: I-5 (Manchester to Vandegrift)--8 freeway lanes to 8 freeway lanes+2 HOV/HOT lanes
| Completed Projects | 1200501 | I-5 North Coast: 4 Express Lanes | On I-5 from La Jolla Village Drive to Vandegrift Boulevard. | Final environmental document and Public Works Plan for four managed lanes including direct access ramps at various locations. | 100% |  | 74.19 | 28.5279 | 45.6621 | Final environmental clearance is 100% complete. | CC004 | CC004: I-5 (SR 52 to I-805)--8 freeway lanes to 6 freeway lanes+4 managed lanes
|  | 1200502 | I-5 HOV Extension & Lomas Santa Fe Interchange | Sorrento Valley Blvd. to Manchester Ave. | Construct northbound HOV lane from Del Mar Heights Road to Manchester Avenue and southbound HOV lane from Sorrento Valley Boulevard to Manchester Avenue. Modify Lomas Santa Fe Avenue interchange and construct auxiliary lanes. | 100% |  | 67.64 | 20.936 | 46.704 | Improvements updated from 4ML to 2ML due to updated state legislation and impact on ENV. | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1200511 | I-5 Ramp Meters | On I-5 from Birmingham Drive to North of Encinitas Boulevard. | Install ramp meters. | 100% |  | 7.313 | 1.69 | 5.623 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1200512 | I-5/Genesee Auxiliary Lane | On I-5 between Genesee Avenue and La Jolla Village Drive. | Design and construction of southbound auxiliary lane on I-5 between Genesee Avenue and La Jolla Village Drive. | 100% |  | 7.243 | 0.132 | 7.111 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 29.
| Remaining Ordinance Projects | 1200504 | I-5 HOV: Manchester Avenue to Palomar Airport Drive | On I-5 from Manchester Avenue to Leucadia Boulevard. | Construct one HOV lane in each direction, soundwalls, a multi-use facility, and a bike path. | 95% |  | 400.627 | 72.271 | 328.356 | Project Limits cover a portion of Ordinance No. 26 and No. 27. | CC007, CC008, CC046 | CC007: I-5 (Via de La Valle to La Costa)--8 freeway lanes to 6 freeway lanes+4 managed lanes CC008: I-5 (La Costa to Cassidy Street), 8 freeway lanes to 6 freeway lanes+4 managed lanes CC046: I-5 (Manchester to Vandegrift), 8 freeway lanes to 8 freeway lanes+2 HOV/HOT lanes
|  | 1200509 | I-5 HOV: San Elijo Bridge Replacement | On I-5 from Lomas Santa Fe Drive to Birmingham Drive. | Construct one HOV lane in each direction, soundwalls, bike trail, and replace the San Elijo Lagoon bridge. | 95% |  | 335.691 | 58.119 | 277.572 | Improvements updated from 4ML to 2ML due to updated state legislation and impact on ENV. | CC007, CC046 | CC007: I-5 (Via de La Valle to La Costa)--8 freeway lanes to 6 freeway lanes+4 managed lanes CC046: I-5 (Manchester to Vandegrift)--8 freeway lanes to 8 freeway lanes+2 HOV/HOT lanes
|  | 1200514 | I-5 HOV Conversion to Express Lanes | On I-5 from the I-5/805 merge to SR-78. | Construction to convert HOV lanes to Express Lanes. | 0% |  | 87 | 3.15 | 83.85 | Future CIP scheduled to begin in FY 2026. | CC005, CC006, CC007, CC008, CC046 | CC005: I-5 (I-805 to SR 56)--8/14 freeway lanes+2 HOV lanes to 6/12 freeway lanes+4 managed lanes CC006: I-5 (SR 56 to Via de La Valle)--8 freeway lanes/10 freeway lanes+2 HOV lanes to 6 freeway lanes/8 freeway lanes+4 managed lanes CC007: I-5 (Via de La Valle to La Costa)--8 freeway lanes to 6 freeway lanes+4 managed lanes CC008: I-5 (La Costa to Cassidy Street)--8 freeway lanes to 6 freeway lanes+4 managed lanes CC046: I-5 (Manchester to Vandegrift)--8 freeway lanes to 8 freeway lanes+2 HOV/HOT lanes
|  | 1200515 | I-5/I-805 HOV Conversion to Express Lanes | On I-805 from SR 52 to the I-5/805 merge and on I-5 from the I-5/805 merge to SR 78. | Corridor study, preliminary engineering and design for the conversion of existing HOV lanes to Express Lanes along the I-5 and I-805 corridors. | 5% |  | 20.303 | 1.953 | 18.35 | Design is 5% complete; construction will be part of a future CIP. Project Limits cover a portion of Ordinance No. 26 and No. 27. | N/A | N/A | Not included in Appendix A
27 |  |  | I-5: Leucadia Blvd to Vandegrift Blvd | Leucadia Blvd. - Vandegrift Blvd | Add 4 managed lanes on I-5 from Leucadia Boulevard to Vandegrift Boulevard. | 31.35% | 370 |  |  |  |  | CC007, CC008, CC046 | CC007: I-5 (Via de La Valle to La Costa)--8 freeway lanes to 6 freeway lanes+4 managed lanes CC008: I-5 (La Costa to Cassidy Street)--8 freeway lanes to 6 freeway lanes+4 managed lanes CC046: I-5 (Manchester to Vandegrift)--8 freeway lanes to 8 freeway lanes+2 HOV/HOT lanes
| Remaining Ordinance Projects | 1200504 | I-5 HOV: Manchester Avenue to Palomar Airport Drive | On I-5 from Leucadia Blvd to Palomar Airport Road. | Construct one HOV lane in each direction, soundwalls, a multi-use facility, and a bike path. | 95% |  | 400.627 | 72.271 | 328.356 | Project Limits cover a portion of Ordinance No. 26 and No. 27. | CC007, CC008, CC046 | CC007: I-5 (Via de La Valle to La Costa)--8 freeway lanes to 6 freeway lanes+4 managed lanes CC008: I-5 (La Costa to Cassidy Street)--8 freeway lanes to 6 freeway lanes+4 managed lanes CC046: I-5 (Manchester to Vandegrift)--8 freeway lanes to 8 freeway lanes+2 HOV/HOT lanes
|  | 1200510 | I-5 HOV: Carlsbad | On I-5 from Palomar Airport Road to north of SR 78. The Batiquitos Lagoon Trail project is located under Interstate 5 from Batiquitos Lagoon Nature Center to Mermaid Lane in the City of Carlsbad. | Construct one HOV lane in each direction and a southbound auxiliary lane at Cannon Road, community enhancement, soundwalls, long-term plant establishment and, as part of the Batiquitos Lagoon Trail project, a new 0.9 east/west trail. | 85% |  | 190.162 | 10.282 | 179.88 | Improvements updated from 4 managed lanes to 2 managed lanes due to updated state legislation and impact on environmental. | CC008, CC046 | CC008: I-5 (La Costa to Cassidy Street)--8 freeway lanes to 6 freeway lanes+4 managed lanes CC046: I-5 (Manchester to Vandegrift)--8 freeway lanes to 8 freeway lanes+2 HOV/HOT lanes
|  | 1200516 | I-5 HOV Lanes: Oceanside | On I-5 from SR 78 to SR 76. | Design of one HOV lane in each direction. | 0% |  | 11.266 | 0.1 | 11.166 | Project will begin in FY 2025. | CC009, CC046 | CC009: I-5 (Cassidy Street to Harbor Drive)--8 freeway lanes to 6 freeway lanes + 4 managed lanes CC046: I-5 (Manchester to Vandegrift)--8 freeway lanes to 8 freeway lanes+ 2 HOV/HOT lanes
28 |  |  | HOV Connector: I-5 / I-805 Interchange | I-5/I-805 Interchange | Addition of a HOV lane connector for the I-5/I-805 interchange. | 0% | 180 | 0 | 0 | 0 | Project has not begun so no progress to date to report. | CC063 | I-5/I-805--North to North and South to South Managed Lane connector
29 |  |  | FWY Connector: I-5 / SR 56 Interchange | I-5/SR 56 Interchange | Addition of a freeway connector for the I-5/SR 56 interchange. | 15% | 140 |  |  |  |  | CC104 | I-5/SR 56--West to North and South to East freeway connector
| Completed Projects | 1200503 | I-5/SR 56 Interchange | At I-5 and SR 56 interchange. | Final environmental document for west-to-north and south-to-east general purpose connectors including auxiliary lanes on SR 56 from El Camino Real to Carmel Country Road. | 100% |  | 12.513 | 0.46276 | 12.0502 | Final environmental document is 100% complete. Design and construction scope remain. | CC104 | I-5/SR 56--West to North and South to East freeway connector
| Remaining Ordinance Projects | TBD | I-5/SR 56 Interchange | At I-5 and SR 56 interchange. | Design and construction of west-to-north and south-to-east general purpose connectors including auxiliary lanes on SR 56 from El Camino Real to Carmel Country Road. | 0% |  | 0 | 0 | 0 | Project has not begun so no progress to date to report. | CC104 | I-5/SR 56--West to North and South to East freeway connector
30 |  |  | FWY Connector: I-5 / SR 78 Interchange | I-5/SR 78 Interchange | Addition of a freeway connector for the I-5/SR 78 interchange. | 6% | 150 |  |  |  |  | CC105, CC064 | CC105: I-5/SR 78--South to East and West to South freeway connector CC064: I-5/SR 78--South to East and West to North, North to East and West to South Managed Lane Connector
| Remaining Ordinance Projects | 1207803 | SR 78/I-5 Express Lanes Connector | At SR 78 and I-5 Connector. | Final environmental document and preliminary engineering for HOV/Managed Lanes direct connectors at SR 78 and I-5. | 10% |  | 66.118 | 16.118 | 50 | Environmental document is 10% complete. | CC105, CC064 | CC105: I-5/SR 78--South to East and West to South freeway connector CC064: I-5/SR 78--South to East and West to North, North to East and West to South Managed Lane Connector
|  | TBD | SR 78/I-5 Express Lanes Connector (Design and Construction) | At SR 78 and I-5 Connector. | Design and construction for HOV/Managed Lanes direct connectors at SR 78 and I-5. | 0% |  | 0 | 0 | 0 | Design has not begun so no progress to date to report. | CC105, CC064 | CC105: I-5/SR 78--South to East and West to South freeway connector CC064: I-5/SR 78--South to East and West to North, North to East and West to South Managed Lane Connector
31 |  |  | Route 398 (COASTER) / BRT Route 472 Improvements | Route 398 COASTER/BRT Route 472 (El Camino Real) | Corridor transit improvements that include a combination of COASTER and BRT projects. COASTER improvements include: vehicles; station improvements including parking, double tracking and other improvements; Del Mar tunnel; and increased service routes. BRT improvements include: vehicles, stations, signal priority and other arterial improvements along El Camino Real, direct access ramps on I-5 south from Encinitas, and increased service routes. | 65.99% | 570 |  |  |  |  | TL05, TL06, TL07 | COASTER improvements
| Completed Projects | 1239801 | Sorrento to Miramar Phase 1 | On coastal rail corridor from Control Point (CP) Pines near Roselle Street to CP Carroll near I-805. | Convert 1.1 miles of single-track to double-track, construct a new bridge, and install new signals. | 100% |  | 45.161 | 31.161 | 14 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1239803 | Oceanside Station Pass-Through Track | On coastal rail corridor at Oceanside Transit Center. | Install third track at station to facilitate train passing and improve operations. | 100% |  | 28.328 | 20.953 | 7.375 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 3.
|  | 1239804 | Carlsbad Double Track | Double track, signals, a new bridge over Agua Hedionda Lagoon, and a universal crossover near CP Farr. | Design double track for the Coastal Rail Corridor from Control Point (CP) Carl to CP Farr in Carlsbad. | 100% |  | 20.2 | 0.226 | 19.974 | Project completed through Design phase. Construction is still pending. | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1239805 | Poinsettia Station Improvements | On coastal rail corridor at Poinsettia Station. | Construct a new grade-separated pedestrian crossing, reconfigure tracks, and install new platform, fence, signals, and track upgrades. | 100% |  | 36.881 | 17.964 | 18.917 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 3.
|  | 1239806 | San Elijo Lagoon Double Track | On coastal rail corridor in Cardiff and across San Elijo Lagoon from Mile Post (MP) 239.2 near Montgomery Avenue to MP 241.3 in Solana Beach. | Install 1.5 miles of new double track, replace Bridge 240.4, reconfigure Control Point Cardiff with double crossovers, install new signals and drainage structures. | 100% |  | 77.787 | 24.0309 | 53.7561 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 3.
|  | 1239808 | Tecolote to Washington Crossovers | On Coastal Rail Corridor from Control Point (CP) Morena near Balboa Avenue to CP Tecolote near Sea World Drive. | Install crossovers to improve staging of trains as they enter Santa Fe Depot. | 100% |  | 8.955 | 2.145 | 6.81 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1239815 | San Diego River Bridge | On the LOSSAN Rail Corridor over San Diego River from Mile Post (MP) 263.2 to MP 264.1 | Construct 0.9 miles of double-track and a new bridge. | 100% |  | 91.746 | 12.6463 | 79.0997 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 3.
|  | 1239817 | Chesterfield Drive Crossing Improvements | On Chesterfield Drive in the City of Encinitas, between Coast Highway 101 and San Elijo Avenue, and in the North County Transit District coastal rail corridor. | Complete final design and construct at-grade crossing improvements including all bike and pedestrian facilities, double track rail, signals, and safety improvements at Chesterfield Drive. | 100% |  | 7.114 | 4.8774 | 2.2366 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 3.
|  | 1239820 | COASTER Train Sets | Along the COASTER corridor. | Two additional train sets to provide more frequent commuter rail service, including 30-minute peak period service, along the COASTER corridor. | 100% |  | 58.8 | 25 | 33.8 |  | TL05 | COASTER improvements
|  | 1239821 | LOSSAN Corridor Improvements | On LOSSAN Rail Corridor from downtown San Diego at Mile Post (MP) 269 to the Orange County Line at MP 207.4. | Includes preliminary engineering, Project Study Reports (PSRs), design criteria and funding applications for complete corridor projects. | 100% |  | 5.02 | 1.02 | 4 | Scope of project is just preliminary engineering and has been completed. | TL06 | COASTER improvements
| Remaining Ordinance Projects | 1239807 | Sorrento Valley Double Track | On coastal rail corridor from Mile Post (MP) 247.8 to MP 248.9 just north of Sorrento Valley Station. | Convert 1.1 miles of single-track to double-track, raise tracks, construct one new bridge and replace one bridge with a culvert, expand parking lot at Sorrento Valley Station, and install new signals. | 95% |  | 32.813 | 3.724 | 29.089 | Project is open to public and working towards completion of Construction Complete milestone. | TL05 | COASTER improvements
|  | 1239809 | Eastbrook to Shell Double Track | On the coastal rail corridor from Control Point (CP) Eastbrook near Oceanside Harbor Drive to CP Shell near Surfrider Way. | Design and final environmental clearance for 0.6 miles of double-track, a new bridge over San Luis Rey River, and new signals. | 14.5% |  | 37.092 | 4.825 | 32.267 | Environmental phase is 95% complete. Overall project (through construction) is 15% complete. | TL06 | COASTER improvements
|  | 1239810 | Carlsbad Village Double Track | On the LOSSAN Rail Corridor from Mile Post (MP) 228.4 near Kelly Street to MP 229.5 near Carlsbad Boulevard across Buena Vista Lagoon and near Carlsbad Village Station | Prepare final environmental document and 30% design for 1.0 miles of double-track, a new bridge across Buena Vista Lagoon, and new signals. | 22.5% |  | 2.733 | 2.353 | 0.38 | Environmental clearance is 100% complete and design is 30% complete. Overall project is 23% complete. | TL06 | COASTER improvements
|  | 1239811 | Elvira to Morena Double Track | On the LOSSAN Rail Corridor from CP Elvira near SR 52 to CP Friar near Friars Road. | Convert 2.6 miles of single-track to double-track and install new signals, replacement bridges, water/sewer facilities, universal crossover at Control Point (CP) Rose, and signaling. | 95% |  | 185.229 | 39.194 | 146.035 | Project is open to public and working towards completion of Construction Complete milestone. | TL05 | COASTER improvements
|  | 1239812 | Sorrento to Miramar Phase 2 | On the LOSSAN Rail Corridor from mile post (MP) 251 near I-805 to MP 253 near Miramar Road. | Final environmental, design and right-of-way activities for 1.9 miles of double-track, curve straightening and new signals. | 37.5% |  | 30.34 | 13.018 | 17.322 | Environmental clearance is 100% complete and design is 90% complete. Overall project is 38% complete. | TL07 | COASTER improvements
|  | 1239813 | San Dieguito Lagoon Double Track and Platform | On the LOSSAN Rail Corridor from the City of Solana Beach Mile Post (MP) 242.2 to south of MP 243.9 in the City of Del Mar | Environmental clearance and design of 2.1 miles of double-track, special events platform, replacement of the San Dieguito Bridge, and other various improvements. Project will be split into two phases for construction. Phase 1 (CIP No. 1239822) will construct 0.8 miles of double-track north of the existing bridge. Phase 2 (CIP No. 1239824) will build the remaining double-track, new bridge, and improvements. | 33.75% |  | 29.697 | 8.586 | 21.111 | Design phase is 75% complete. Overall project is 34% complete. Construction will occur on 1239822 and 1239824. | TL06 | COASTER improvements
|  | 1239814 | LOSSAN Rail Corridor Preliminary Engineering | On the LOSSAN Rail Corridor from Santa Fe Depot to Stuart Mesa Maintenance Facility. | Conduct preliminary engineering for prioritization of LOSSAN Rail Corridor improvement projects. Preparation of Project Study Reports (PSRs), design criteria, standard plans and funding applications to better define future projects. | 80% |  | 1.724 | 1.724 | 0 | Scope of project is just preliminary enginnering (PE). PE is 80% complete. | TL05 | COASTER improvements
|  | 1239816 | Batiquitos Lagoon Double Track | On the LOSSAN Rail Corridor over Batiquitos Lagoon from Mile Post (MP) 234.5 to MP 235.5 | Construct 0.8 miles of double-track and a new bridge over Batiquitos Lagoon. | 40% |  | 165.627 | 46.577 | 119.05 | Project is complete through environmental and design phases. Construction will begin in FY 2025. | TL06 | COASTER improvements
|  | 1239819 | Carlsbad Village Double Track Trench | On coastal rail corridor in south Oceanside and Carlsbad, from Mile Post (MP) 228.0 to MP 230.6, through Carlsbad's downtown village area. | Preliminary engineering and environmental clearance for a double track railroad trench, 1.1 miles of second main track, and replacement of railroad lagoon Bridge 228.6. | 5% |  | 21.181 | 0.1076 | 21.0734 | Alternatives analyses complete. Environmental clearance will resume in FY 2026 when STIP funds become available. | TL06 | COASTER improvements
|  | 1239822 | San Dieguito Lagoon Double Track Phase 1 Construction | On the LOSSAN Rail Corridor from City of Solana Beach (Mile Post [MP] 242.2) to north of the San Dieguito River Bridge (MP 242.9). | Construct 0.8 miles of double-track and other various improvements. | 0% |  | 62.328 | 6 | 56.328 | Construction will begin in FY 2025. | TL06 | COASTER improvements
|  | 1239823 | San Dieguito to Sorrento Valley Double-Track | Within the City of Del Mar and the City of San Diego from Control Point (CP) Valley at Mile Post (MP) 242 to CP Sorrento at MP 249.1. | Completion of Project Approval and Environmental Document (PA&ED) phase re-aligning the LOSSAN Rail Corridor away from the Del Mar Bluffs with a double-track system, and the advancement of the design and right-of-way phases. | 9% |  | 302.718 | 2.718 | 300 | Environmental clearance is 40% complete. Overall project through construction is 9% complete. | TL06 | COASTER improvements
|  | 1239824 | San Dieguito Lagoon Double-Track Phase 2 Construction | In the City of Del Mar, along the San Diego subdivision of the LOSSAN Rail Corridor between Mile Post (MP) 243.0 to MP 243.9. | Construction of 0.3 miles of new main track, improvements to 0.6 siding track, the replacement of aging wood trestle San Dieguito Lagoon Rail Bridge, construction of special events platform for the Del Mar Fairgrounds, and other various improvements. | 0% |  | 255.809 | 8.844 | 246.965 | Construction will begin in FY 2025. | TL06 | COASTER improvements
32 |  |  | SR 52: I-15 to SR 125 | I-15 to SR 125 | Add 2 freeway lanes and 2 reversible managed lanes on SR 52 from I-15 to SR 125. | 53.5% | 170 |  |  |  |  | CC030, CC031 | CC030: SR 52 (I-15 to Mast Boulevard)--6 freeway lanes to 4 freeway lanes+ 3 managed lanes CC031: SR 52 (Mast Boulevard to SR 125)--4 freeway lanes to 4 freeway lanes+ 3 managed lanes
| Completed Projects | 1205201 | SR 52 Managed Lanes | In San Diego and Santee from I-15 to SR 125. | Preliminary environmental analyses for SR 52 two reversible managed lane project. | 100% |  | 6.972 | 6.823 | 0.149 | Project included preliminary engineering analyses only. | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1205202 | SR 52 Widening | On SR 52 in San Diego from I-15 to Mast Boulevard. | Construct third eastbound and westbound lane between I-15 and Mast Boulevard, including landscaping. | 100% |  | 41.745 | 38.745 | 3 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
| Remaining Ordinance Projects | 1205204 | SR 52 Improvements | Along SR 52 from I-805 to SR 125. | Environmental clearance and design for operational improvements along SR 52. Design phase includes planning for transit opportunities in the SR 52 corridor. | 7% |  | 17.5 | 6 | 11.5 | Environmental document is 20% complete. Entire project, considering future planned construction, is 7% complete. | CC030, CC031 | CC030: SR 52 (I-15 to Mast Boulevard)--6 freeway lanes to 4 freeway lanes+ 3 managed lanes CC031: SR 52 (Mast Boulevard to SR 125)--4 freeway lanes to 4 freeway lanes+ 3 managed lanes
33 |  |  | SR 52: SR 125 to SR 67 | SR 125 to SR 67 | Add 4 freeway lanes on SR 52 from SR 125 to SR 67. | 100% | 240 |  |  |  |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
| Completed Projects | 1205203 | SR 52 Extension | On SR 52 from SR 125 to SR 67. | Construct four general purpose lanes, direct connectors at SR 125 and SR 67, and interchanges at Fanita Drive, Magnolia Avenue, and Cuyamaca Street. | 100% |  | 460.509 | 110.994 | 349.515 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
34 |  |  | FWY Connector: SR 94 / SR 125 Interchange | SR 94 / SR 125 interchange | Freeway connector for the SR 94 / SR 125 interchange. | 35% | 110 |  |  |  |  | CC108 | SR 94 / SR 125, South to East freeway connector, including aux lane to Lemon Avenue
| Remaining Ordinance Projects | 1212501 | SR 94/SR 125 South to East Connector | On SR 94 and SR 125 from Lemon Avenue to Bancroft Drive. | Design and right-of-way of southbound SR 125 to eastbound SR 94 direct connector. Construction of operational improvements on SR 125 Northbound Auxiliary Lane, SR 125 Southbound Auxiliary Lane, and SR 94 Eastbound Auxiliary Lane (Phase 1). Phase 2 will include construction of the southbound SR 125 to eastbound SR 94 direct connector. | 35% |  | 135.24 | 3.914 | 131.326 | Environmental document is complete and design phase is 80% complete. Entire project, considering future planned construction, is 35% complete. | CC108 | SR 94 / SR 125, South to East freeway connector, including aux lane to Lemon Avenue
|  | 1612501 | CMCP - High Speed Transit/SR 125 | On SR 125 from SR 52 to SR 905 and the U.S.-Mexico Border. | Development of multimodal transportation solutions to improve mobility in the corridor along SR 125 from SR 52 to SR 905 and the U.S.-Mexico border. The Comprehensive Multimodal Corridor Plan (CMCP) also will include analysis of tolls on the South Bay Expressway. | 10% |  | 3.692 | 0.165 | 3.527 | CMCP study is 10% complete. Project does not include environmental clearance, design, or construction phases. | CC108 | SR 94 / SR 125, South to East freeway connector, including aux lane to Lemon Avenue
35 |  |  | SR 94: SR 125 to Steele Canyon Rd | SR 125 to Steele Canyon Rd | Widen to six lanes from SR 125 to Avocado Boulevard and expand to a continuous four-lane facility from Avocado Boulevard to Steele Canyon Road, including environmental enhancements from Jamacha Road to Steele Canyon Road. | 0% | 90 |  |  |  | Project has not begun so no progress to date to report. | Not included | N/A
36 |  |  | SR 94 / SR 125: I-805 to I-8 | I-805 to I-8 | Add two HOV lanes from I-805 to I-8. | 0% | 350 |  |  |  |  | CC034, CC042 | C034: SR 94 (I-805 to SR 125)--8 freeway lanes to 6 freeway lanes+3 managed lanes CC042: SR 125 (SR 54 to Amaya Drive)--6/8 freeway lanes to 4/6 freeway lanes+ 2 managed lanes
| Remaining Ordinance Projects | 1609401 | CMCP - High Speed Transit/SR 94 | Along the SR 94 corridor from I-5 to SR 125. | Development of multimodal transportation solutions to increase transportation options, decrease congestion, and improve mobility along SR 94 between I-5 and SR 125 in San Diego, from Downtown San Diego to Lemon Grove. | 0% |  | 2.226 | 0.206 | 2.02 | CMCP study will begin in FY 2025. | N/A | N/A
|  | TBD | SR 94 / SR 125: I-805 to I-8 | I-805 to I-8 | Final environmental document, design, and construction of two HOV lanes from I-805 to I-8. | 0% |  | 0 | 0 | 0 | Final environmental document has not begun so no progress to date to report. | CC034, CC042 | C034: SR 94 (I-805 to SR 125)--8 freeway lanes to 6 freeway lanes+3 managed lanes CC042: SR 125 (SR 54 to Amaya Drive)--6/8 freeway lanes to 4/6 freeway lanes+ 2 managed lanes
37 |  |  | Route 520 (Orange Line Trolley) Improvements | Downtown San Diego to Arnele Avenue in El Cajon | Conversion to low-floor vehicles, enhanced stations, signal upgrades, and extended platforms. | 92.73% | 70 |  |  |  |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
| Completed Projects | 1210010 | Orange and Blue Line Project Management | On trolley system from Old Town Transit Center, La Mesa Station, San Ysidro Station to downtown San Diego. | Coordinate budget, schedule, environmental clearance, permitting, design, construction, and construction management for conversion to low-floor vehicles and system renewal. | 100% |  | 19.429 | 18.918 | 0.511 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1210040 | Orange and Blue Line Traction Power Substations | Blue Line: from America Plaza to San Ysidro, Orange Line: from Santa Fe Depot to Grossmont. | Install 17 new traction power substations; site improvements at stations and substations and network improvements. | 100% |  | 29.2 | 15.5044 | 13.6956 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1210050 | Orange and Blue Line Communications System | Blue Line: from America Plaza to San Ysidro; Orange Line: from Santa Fe Depot to Grossmont; Green Line: from Old Town to 12th & Imperial. | Install communications equipment including variable message signs, central control software, fiber optic cable, real-time next Trolley arrival signs, and closed-circuit television. | 100% |  | 5.979 | 4.992 | 0.987 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1210070 | Orange and Blue Line Platforms | Blue Line: from America Plaza to San Ysidro; Orange Line: from Santa Fe Depot to Grossmont; Green Line: from Old Town to 12th & Imperial. | Reconstruct station platforms for low-floor Trolley vehicles and replace existing shelters. Install a double crossover at America Plaza Station and replace switches and signaling system at Santa Fe Depot. | 100% |  | 69.216 | 32.072 | 37.144 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1210080 | Low Floor LRT Vehicles | Blue Line: from America Plaza to San Ysidro; Orange Line: from Santa Fe Depot to Grossmont; Green Line: from Old Town to 12th & Imperial. | 65 new low-floor trolley vehicles. | 100% |  | 269.057 | 36.921 | 232.136 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
| Remaining Ordinance Projects | 1210090 | Low-Floor Light Rail Transit Vehicles | 47 Light Rail Vehicles (LRVs) to replace existing SD100 fleet to support additional, more frequent trolley service. | New low-floor vehicle procurement for San Diego Trolley system. | 53.19% |  | 72.26 | 30.26 | 42 | 25 out of the 47 vehicles (53%) have been delivered, accepted, and put into service. | N/A | N/A
38 |  |  | SR 54 / SR 125: I-805 to SR 94 | I-805 to SR 94 | Add two lanes to provide a continuous facility with three general purpose lanes and one HOV lane in each direction. | 0% | 140 | 0 | 0 | 0 | Project has not begun so no progress to date to report. | CC040, CC042 | CC040: SR 54 (I-805 to SR 125), 6 freeway lanes to 4 freeway lanes+2 managed lanes CC042: SR 125 (SR 54 to Amaya Drive), 6/8 freeway lanes to 4/6 freeway lanes+2 managed lanes
39 |  |  | SR 67: Mapleview St to Dye Rd | Mapleview St to Dye Rd | Expand to a continuous four-lane facility, including environmental enhancements, from Mapleview Street to Dye Road. | 3% | 240 |  |  |  |  | CC050 | SR 67 (Mapleview to Dye Road)--Shoulder Widening/Straightening; new lanes will be for use during emergencies only
| Completed Projects | 1605201 | CMCP - Coast, Canyons, and Trails (SR 52) | Along the SR 52 from I-5 to SR 67 and along SR 67 from I-8 to Mapleview Street. | Oversight of utilization of data in transportation planning and development of multimodal projects and strategies that integrate active transportation, transit, and the deployment of technology to better manage mobility throughout the corridor. | 100% |  | 2.106 | 0.334 | 1.772 | CMCP study is complete. Project does not include environmental clearance, design, or construction phases. | N/A | N/A | Not included in Appendix A
|  | 1606701 | CMCP - San Vicente Corridor (SR 67) | Along SR 67 from Mapleview Street in the coummnity of Lakeside, and including SR 78 in the community of Ramona. | A Comprehensive Multimodal Corridor Plan (CMCP) is a comprehensive, integrated management plan for increasing transportation options, decreasing congestion, and improving travel times in a transportation corridor. | 100% |  | 0.99093 | 0.01792 | 0.97301 | CMCP study is complete. Project does not include environmental clearance, design, or construction phases. | N/A | N/A | Not included in Appendix A
| Remaining Ordinance Projects | 1206701 | SR 67 Improvements | Along SR 67 from Mapleview Street to Dye Road in San Diego County. | Environmental clearance and design for alternatives to enhance temporary evacuation capacity along SR 67, including transit options from Ramona to Poway. | 3% |  | 52 | 3.832 | 48.168 | Preliminary engineering is 60% complete. Entire project, considering future environmental clearance, design, and construction, is 3% complete. | CC050 | SR 67 (Mapleview to Dye Road)--Shoulder Widening/Straightening; new lanes will be for use during emergencies only
40 |  |  | I-8: Second St to Los Coches Rd | Second St to Los Coches Rd | Add two general purpose lanes from Second Street to Los Coches Road. | 5% | 30 |  |  |  |  | CC027 | I-8 (Mollison Avenue to Greenfield Drive)--4/6 freeway lanes to 4 freeway lanes+4 managed lanes
| Completed Projects | 1600801 | CMCP - High Speed Transit/I-8 | Along the I-8 corridor from San Diego Bay to Lakeside. | Oversight of utilization of data in transportation planning and development of multimodal transportation solutions to increase transportation options, decrease congestion, and improve mobility along the I-8 Corridor. It will also consider future transportation connections to the proposed SDSU Mission Valley Campus development. | 100% |  | 3 | 0.195 | 2.805 | CMCP study is complete. Project does not include environmental clearance, design, or construction phases. | N/A | N/A | Not included in Appendix A
| Remaining Ordinance Projects | TBD | I-8: Second St to Los Coches Rd | Second St to Los Coches Rd | Final environmental document, design, and construction of two general purpose lanes. | 0% |  | 0 | 0 | 0 | Final environmental document has not begun so no progress to date to report. | CC027 | I-8 (Mollison Avenue to Greenfield Drive)--4/6 freeway lanes to 4 freeway lanes+4 managed lanes
41 |  |  | SR 78: I-5 to I-15 | I-5 to I-15 | Add 2 HOV lanes on SR 78 from I-5 to I-15. | 6% | 500 |  |  |  |  | CC036, CC037 | CC036: SR 78 (I-5 to Twin Oaks)--6 freeway lanes to 4 freeway lanes+4 managed lanes+connectors CC037: SR 78 (Twin Oaks to I-15)--6 freeway lanes to 4 freeway lanes+4 managed lanes
| Completed Projects | 1201510 | SR 78 Nordahl Road Interchange | On SR 78 at Nordahl Road. | Replace Nordahl Road bridge over SR 78 and construct a new westbound lane on SR 78 between I-15 and Nordahl Road. | 100% |  | 23.804 | 16.577 | 7.227 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1207801 | SR 78 HOV/Managed Lanes (Study Only) | On SR 78 from I-5 to I-15. | Preliminary engineering for HOV/managed lanes in the median of SR 78. | 100% |  | 1.683 | 1.683 | 0 | Scope only included project study report. Environmental clearance and future design/construction will take place on 1207804. | N/A | N/A | Project completed prior to 2015 Regional Plan.
| Remaining Ordinance Projects | 1207803 | SR 78/I-5 Express Lanes Connector | At SR 78 and I-5 Connector. | Final environmental document and preliminary engineering for HOV/Managed Lanes direct connectors at SR 78 and I-5. | 6% |  | 66.118 | 16.118 | 50 | Environmental phase is 10% complete. Overall project is 6% complete when considering future design and construction phases. | CC036 | CC036: SR 78 (I-5 to Twin Oaks)--6 freeway lanes to 4 freeway lanes+4 managed lanes+connectors
|  | 1207804 | SR 78 HOV Lanes: I-5 to I-15 | On SR 78 from I-5 to I-15. | Environmental studies and preliminary engineering for HOV/Managed Lanes along SR 78. | 6% |  | 39 | 30 | 9 | Environmental phase is 10% complete. Overall project is 6% complete when considering future design and construction phases. | CC036, CC037 | CC036: SR 78 (I-5 to Twin Oaks)--6 freeway lanes to 4 freeway lanes+4 managed lanes+connectors CC037: SR 78 (Twin Oaks to I-15)--6 freeway lanes to 4 freeway lanes+4 managed lanes
42 |  |  | Route 399 (SPRINTER) / BRT Route 471 Improvements | Regionwide improvements | Corridor transit improvements that include a combination of SPRINTER and BRT projects. SPRINTER improvements include: double tracking, North County Fair extension, some grade separations, 15-minute peak service by 2016, and 15-minute all day service by 2030. BRT improvements include: vehicles, signal priority and other arterial improvements, building 18 stations, and 15-minute peak / 30-minute off peak service by 2020. | 25% | 200 |  |  |  |  | TL10, TL11, TL39 | SPRINTER improvements and Rapid Route 471
| Completed Projects | 1230001 | SPRINTER | SPRINTER rail transit service between Oceanside and Escondido. | Construct 15 stations and operates diesel multiple unit (DMU) rail vehicles on double- and single-track right-of-way from Oceanside to Escondido and servicing the Oceanside Transit Center and Escondido Transit Center. | 100% |  | 65.87 | 65.87 | 0 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
| Remaining Ordinance Projects | 1607801 | CMCP - SPRINTER/Palomar Airport Road/SR 78/SR 76 | Between the I-5 and I-15 freeways, along the SR 76, SR 78, Palomar Airport Road and the SPRINTER rail corridor. | Oversight of utilization of data in transportation planning and development of multimodal transportation solutions to improve connectivity and access to homes, jobs, and education hubs in North County by reducing travel times, creating greater trip reliability and providing travelers with more transportation choices. | 100% |  | 3 | 0.405 | 2.595 |  | TL10, TL11, TL39 | SPRINTER improvements and Rapid Route 471
|  | TBD | BRT Route 471 Improvements | Regionwide improvements | BRT improvements include: vehicles, signal priority and other arterial improvements, building 18 stations, and 15-minute peak / 30-minute off peak service by 2020. | 0% |  | 0 | 0 | 0 | Project has not begun so no progress to date to report. | TL10, TL11, TL39 | SPRINTER improvements and Rapid Route 471
43 |  |  | SR 76: Melrose Dr to I-15 | Melrose Dr to I-15 | Add two general purposes lanes on SR 76 from Melrose Drive to I-15, including environmental enhancements from Mission Road to I-15. | 100% | 180 |  |  |  |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 7.
| Completed Projects | 1207602 | SR 76 Middle | On SR 76 from Melrose Drive to Mission Road. | Reconstruct two-lane conventional highway as a four-lane conventional highway. | 100% |  | 165.075 | 57.163 | 107.912 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1207606 | SR 76 East | On SR 76 from Mission Road to I-15. | Reconstruct two-lane conventional highway as a four-lane conventional highway and modify the SR 76/I-15 Interchange. | 100% |  | 202.691 | 67.613 | 135.078 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 7.
44 |  |  | SR 56: I-5 to I-15 | I-5 to I-15 | Add one general purpose lane on SR 56 in each direction from I-5 to I-15. | 23% | 100 |  |  |  |  | CC035 | SR 56 (I-5 to I-15)-- 4 freeway lanes to 4 freeway lanes+ 3 managed lanes
| Remaining Ordinance Projects | 1200513 | SR 56 HOV Lanes | On SR 56 from El Camino Real to Carmel Valley Road. | Construct one HOV lane in each direction on SR 56 from El Camino Real (I-5) to Carmel Valley Road. | 46% |  | 27.944 | 1.391 | 26.553 | Construction is 10% complete. Overall project scope, considering environmental clearance and design, is 46% complete. | CC035 | SR 56 (I-5 to I-15)-- 4 freeway lanes to 4 freeway lanes+ 3 managed lanes
|  | 1605601 | CMCP - High Speed Transit/SR 56 | Along the SR 56 corridor from I-5 to I-15. | A Comprehensive Multimodal Corridor Plan (CMCP) is a comprehensive, integrated management plan for increasing transportation options, decreasing congestion, and improving travel times in a transportation corridor. | 0% |  | 1.1 | 0 | 1.1 | Future CIP scheduled to begin in FY 2026. | CC035 | SR 56 (I-5 to I-15)-- 4 freeway lanes to 4 freeway lanes+ 3 managed lanes
|  | TBD | SR 56 HOV Lanes Phase 2 | On SR 56 from Carmel Valley Road to I-15. | Construct one HOV lane in each direction on SR 56 from Carmel Valley Road to I-15. | 0% |  | 0 | 0 | 0 | This second half of Ordinance 44 has not started. | CC035 | SR 56 (I-5 to I-15)-- 4 freeway lanes to 4 freeway lanes+ 3 managed lanes
45 |  |  | BRT Showcase Route 611: via El Cajon Blvd & Park Blvd (Now known as Mid-City Rapid Route 215) | El Cajon Blvd & Park Blvd | Signal priority, queue jumper lanes, other arterial improvements, vehicles; builds 13 stations and incorporates upgrades to downtown stations. 10-minute peak / 15-minute off-peak service by 2006. | 100% | 170 |  |  |  |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 53.
| Completed Projects | 1201507 | SR 15 BRT: Mid-City Centerline Stations | On SR 15 at University Avenue and El Cajon Boulevard. | Construct two bus rapid transit (BRT) stations in the median of SR 15. | 100% |  | 61.673 | 38.5234 | 23.1496 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 53.
|  | 1240001 | Mid-City Rapid Bus | From San Diego State University to Downtown San Diego along El Cajon Boulevard, College Avenue, Park Boulevard, and Broadway, including Rapid stations located along SR 15 at the El Cajon Boulevard and University Avenue ramps. | Provide new Rapid Bus service including: consolidated transit stops, SR 15 transit plaza and Mid-City Centerline, synchronized traffic signals with extended green lights for buses, new low-floor vehicles, new shelters, improve waiting areas, real-time next-bus arrival signs, service frequency upgrade to every 10 minutes in the peak period, and every 15 minutes off-peak. Additional improvements include adding Traffic Signal Priority (TSP) along Park Boulevard, and TSP maintenance reporting for Rapid Fleet. | 100% |  | 44.526 | 21.8272 | 22.6988 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
46 |  |  | SR 75 / SR 282 (Coronado Tunnel): Glorietta Blvd to Alameda Blvd | Glorietta Blvd to Alameda Blvd | Provide matching funds for construction purposes only for a tunnel from Glorietta Boulevard to Alameda Boulevard. | 0% | 25 | 0 | 0 | 0 | Project has not begun so no progress to date to report. | Not included
47 |  |  | Border Access Improvements | San Diego/Mexico Border | Provide matching construction funds for access improvements in the international border area. | 62.5% | 25 |  |  |  |  | CC045, CC148, GM01, GM03, TL47, TL53, TL59 | Roadway and transit improvements at Otay Mesa and Otay Mesa East
| Completed Projects | 1201102 | SR 11 and Otay Mesa East Port of Entry: Segment 1 Construction | On new alignment from SR 125 to Enrico Fermi Drive. | Construct SR 11 four-lane highway from SR 125 to Enrico Fermi Drive. | 100% |  | 65.56 | 0 | 65.56 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 53.
|  | 1201103 | SR 11 and Otay Mesa East Port of Entry: Segment 2A and SR 905/125/11 Southbound Connectors Construction | On new alignment from Enrico Fermi Drive to Otay Mesa Port of Entry and at SR 905/125/11 interchange | Construct SR 11 four-lane toll highway from Enrico Fermi Drive to the proposed Otay Mesa East Port of Entry, and the SR 125 southbound to eastbound SR 905 and eastbound SR 11 connectors. | 100% |  | 127.769 | 0 | 127.769 |  | CC045 | SR 11/Otay Mesa East Port of Entry (Enrico Fermi to Mexico)--4 tolls and port of entry
|  | 1201104 | SR 11 and Otay Mesa East Port of Entry: Siempre Viva Interchange Construction | On SR 11 at Siempre Viva Road. | Construction of Siempre Viva interchange. | 100% |  | 22.995 | 0 | 22.995 |  | CC045 | SR 11/Otay Mesa East Port of Entry (Enrico Fermi to Mexico)--4 tolls and port of entry
|  | 1201105 | SR 11 and Otay Mesa East Port of Entry: Traffic and Revenue Study | On new alignment from SR 125 to the U.S.-Mexico Border. | Develop an Investment Grade Traffic and Revenue (IG T&R) study for the SR 11/Otay Mesa East Port of Entry project. | 100% |  | 4.3 | 1.8 | 2.5 | Project scope is just for traffic and revenue study. No construction activity occurred under this CIP. | CC045 | SR 11/Otay Mesa East Port of Entry (Enrico Fermi to Mexico)--4 tolls and port of entry
|  | 1201106 | Otay Mesa East Port of Entry Utility Improvements | On State Route 11 at 1.9 miles east of Sanyo Avenue Undercrossing. | Design and construct new utility services including water, sewer, communication, electrical, and gas that will facilitate operations for the future Otay Mesa East POE and CHP-operated Commercial Vehicle Enforcement Facility. | 100% |  | 9.142 | 0 | 9.142 |  | GM01 | Otay Mesa Commercial Vehicle Enforcement Facility (CVEF) Modernization
|  | 1300601 | San Ysidro Intermodal Freight Facility | At San Ysidro freight yard near East San Ysidro Boulevard and U.S. Port of Entry. | Purchase right-of-way, add storage tracks, and construct truck-loading staging area. | 100% |  | 40.35 | 4.802 | 35.548 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 5.
|  | 1300602 | South Line Rail Freight Capacity | On Trolley system from Palomar Street station to San Ysidro station. | Install communication enhancements, crossovers, and signals. | 100% |  | 47.231 | 7.718 | 39.513 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 3.
|  | 1390501 | SR 905: I-805 to Britannia Boulevard | On new alignment from I-805 to Britannia Boulevard. | Construct six-lane freeway. | 100% |  | 85.637 | 1.582 | 84.055 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1390502 | I-805/SR 905 Connectors | At SR 905 and I-805 Interchange. | Widen west to north ramp connector. | 100% |  | 17.372 | 0 | 17.372 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1390505 | SR 905/125/11 Southbound Connectors | At SR 905/125/11 Interchange. | Design of SR 125 connectors southbound to eastbound SR 905 and eastbound SR 11. | 100% |  | 7.5 | 0 | 7.5 | Project scope was for design phase only. Construction took place on CIP 1201103. | CC045 | SR 11/Otay Mesa East Port of Entry (Enrico Fermi to Mexico)--4 tolls and port of entry
|  | 1390506 | SR 125/905 Southbound to Westbound Connector | At SR 125/905 Interchange. | Construct SR 125/905 southbound to westbound freeway grade-separated interchange connector. | 100% |  | 28.992 | 0 | 28.992 |  | CC148 | SR 125 (SR 905)--South to West Managed Lane Connector
| Remaining Ordinance Projects | 1201101 | SR 11 and Otay Mesa East Port of Entry | On new alignment from SR 125 to the U.S.-Mexico Border. | Design and right-of-way (ROW) for four-lane toll highway from SR 125 to proposed Port of Entry (POE), including the proposed Commercial Vehicle Enforcement Facility (CVEF) and POE at the Mexico border. Construction of CVEF, POE, and tolling system. Prepare engineering studies for the Otay Mesa East POE and tolling system. SR 11 Otay East Bridging Document - 30% Architectural Plans, Bond Counsel, Documents Required for Bond Issuance. | 25% |  | 614.602 | 40.839 | 573.763 | Project is 40% complete through design. Overall project scope is 25% complete. | CC045, GM01, GM03, TL53, TL59, TL47 | Roadway and transit improvements at Otay Mesa and Otay Mesa East
48 |  |  | SR 125: SR 905 to SR 54 | SR 905 to SR 54 | South Bay Expressway toll road purchase. | 100% | N/A |  |  |  |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
| Completed Projects | 1390502 | I-805/SR 905 Connectors | At SR 905 and I-805 Interchange. | Widen west to north ramp connector. | 100% |  | 17.372 | 0 | 17.372 |  | N/A | N/A | Project completed prior to 2015 Regional Plan.
|  | 1390504 | SR 905/125/11 Northbound Connectors | At SR 905/125/11 Interchange. | Construct northbound connectors to SR 125 from eastbound SR 905, westbound SR 905, and westbound SR 11. | 100% |  | 18.757 | 2.7 | 16.057 |  | N/A | N/A | Project completed prior to 2021 Regional Plan. Last included in 2015 Regional Plan, Appendix A page 34.
|  | 3312100 | South Bay Expressway (Toll Road Purchase) | SR 125 toll road | South Bay Expressway toll road purchase. | 100% |  | - | - | - |  | N/A | N/A | Project completed prior to 2015 Regional Plan.